## Sheet1
Date | Requirements Gathering | High Level Design | Low Level Design | Development | Testing | Requirement | Hours to complete | Date completed | Category
2021-09-10 | 10 | 4 | 16 | 75 | 20 | Requirements document | 5 | 2021-09-17 | Requirements Gathering
2021-09-24 | 0 | 4 | 16 | 75 | 12 | Project Plan | 5 | 2021-09-17 | Requirements Gathering
2021-10-08 | 0 | 0 | 0 | 75 | 12 | Debugging Page | 8 | 2021-09-22 | Testing
2021-10-22 | 0 | 0 | 0 | 68 | 8 | Class Diagrams | 5 | 2021-10-04 | Low Level Design
2021-11-05 | 0 | 0 | 0 | 43 | 4 | Activity Diagrams | 5 | 2021-10-04 | Low Level Design
2021-11-19 | 0 | 0 | 0 | 10 | 0 | Database drinkDemo Prototype | 6 | 2021-10-04 | Low Level Design
2021-12-03 | 0 | 0 | 0 | 0 | 0 | UI Prototypes | 4 | 2021-10-04 | High Level Design
[6 empty] | Home & Login Pages | 4 | 2021-10-20 | Development
[6 empty] | Development Sprint 1 Testing | 4 | 2021-10-20 | Testing
[6 empty] | Calender Implementation | 3 | 2021-10-22 | Development
[6 empty] | Authentication | 15 | 2021-10-26 | Development
[6 empty] | User Database | 10 | 2021-10-26 | Development
[6 empty] | Development Sprint 2 Testing | 4 | 2021-11-03 | Testing
[6 empty] | Scoresheet page | 2 | 2021-11-09 | Development
[6 empty] | Drink Order Page | 2 | 2021-11-09 | Development
[6 empty] | Manage Tournament Page | 2 | 2021-11-09 | Development
[6 empty] | User Dashboards | 10 | 2021-11-10 | Development
[6 empty] | Page Security | 2 | 2021-11-11 | Development
[6 empty] | Managers can manage user types | 5 | 2021-11-11 | Development
[6 empty] | Sponsor Dashboard | 5 | 2021-11-12 | Development
[6 empty] | Tournament Functionality | 5 | 2021-11-14 | Development
[6 empty] | Development Sprint 3 Testing | 4 | 2021-11-17 | Testing
[6 empty] | Styling | 10 | 2021-11-22 | Development
125